## Report
Procurement Performance Monitoring Indicator
<Name of the Implementing Agency>
Reporting Period (Quarterly) ………………..
SN | Indicator Category | Process Indicator | Performance Data |  | Remarks
|  |  | Definition | Result*
1 | Invitation for bid | Advertisement of bid opportunities in newspaper | 1. Percentage of invitation for bid (IFB) published in newspaper | 100%
|  | Advertisement of bid opportunities in CPTU’s website | 2. Percentage of invitation for bid (above threshold) advertised in CPTU’s website | 75% | needs improvement
|  | Contracts following GoB procurement rules | 3. Percentage of contracts following GoB procurement rules | 60% | 100% complied
|  | Contracts following development partner rules | 4. Percentage of contracts following development partner rules | 40% | 100% complied
2 | bid Submission | Multiple locations submission bids | 5. Percentage of bids allowed to submit in multiple locations | 0% | 100% complied
|  | Bid preparation time in open bidding method | 6. Average number of days between publishing of advertisement and bid submission deadline | 38.6 | mixture of ICB and NCB
|  | Bid time compliance | 7. Percentage of bids having sufficient bid submission time | 80% | needs improvement
|  | Sale of bid documents | 8. Average number of bidders purchased bid documents | 11
|  | Bidder participation | 9. Average number of bidders submitted bids | 6
|  | Bidder participation index | 10. Ratio of number of bid submission and number of bid document sold | 0.54545
3 | bid Opening Committee (BOC) and bid Evaluation Committee (BEC) | Bid opening committee formation | 11. Percentage of cases BOC included at least ONE member from BEC | 100%
|  | Bid evaluation committee formation | 12. Percentage of cases BEC formed by Contract Approving Authority | 80% | needs improvement
|  | External member in BEC | 13. Percentage of cases BEC included TWO external members outside the procuring entity | 80% | needs improvement
4 | bid Evaluation | Bid evaluation time | 14. Average number of days between bid opening and completion of evaluation | 113.6
|  | Compliance of bid evaluation time | 15. Percentage of cases bid evaluation has been completed within timeline | 0%
|  | Bid acceptance | 16. Average number of responsive bids | 2.2
|  | Re-bidding | 17. Percentage of cases BEC recommended for re-bidding | 0%
|  | Bid cancellation | 18. Percentage of cases where bid process cancelled | 20%
5 | Bid Evaluation Report (BER) approval | bid Evaluation Approval time | 19. Average number of days taken between submission of bid evaluation and approval of contract (contract signing date) | 40
|  | Compliance of financial delegation | 20. Average number of bids approved by the proper financial delegated authority | 100%
|  | Submission of evaluation report to appropriate authority | 21. Percentage of cases BEC submitted report directly to the contract approving authority | 80%
|  | BER approval compliance | 22. Percentage of cases contract award decision made within timeline by contract approving authority | 80%
|  | Additional review of BER | 23. Percentage of cases BER reviewed by person/committee other than the contract approving authority | 0%
|  | Higher tier approval | 24. Percentage of bids approved by higher tier than the contract approving authority | 20%
6 | Contract Award | Time for issuance of NOA to bidder | 25. Average number of days between final approval and notification of award (NOA) | 6.2
|  | Bid processing lead time | 26. Average number of days between bid opening and notification of award (NOA) | 150.8
|  | Total bid processing time | 27. Average number of days between invitation for bid (IFB) and notification of award | 189.4
|  | Publication of award information | 28. Percentage of contract awards published in CPTU’s website | 100%
|  | Efficiency in Contract Award | 29. Percentage of contracts awarded within initial bid validity period | 40% | needs improvement
7 | Delivery/Completion | Delivery time | 30. Percentage of contracts completed/ delivered within the original schedule as mentioned in the contract | 0%
|  | Liquidated damage | 31. Percentage of contracts having liquidated damage imposed for delayed delivery/completion | 0%
|  | Completion rate | 32. Percentage of contracts fully completed and accepted | 0%
8 | Payment | Payment release compliance | 33. Average number of days taken to release payment | 0
|  | Late payment | 34. Percentage of cases (considering each installment as a case) with delayed payment | 0%
|  | Interest paid for delayed payment | 35. Percentage of Contracts where interest for delayed payments was made | #DIV/0!
9 | Complaints | bid procedure complaints | 36. Percentage of bid procedures with complaints | 21.43%
|  | Resolution of complaints with award modification | 37. Percentage of complaints resulting in modification of award | 0%
|  | Resolution of complaints | 38. Percentage of cases complaints have been resolved | 21.43%
|  | Independent Review Panel | 39. Percentage of cases review panel’s decision upheld | N/A
10 | Contract amendments | Contract Amendment/variation | 40. Percentage of contract amendments/variations | 7.143%
11 | Contract dispute resolution | Unresolved Disputes | 41. Percentage of Contracts with unresolved disputes | 14.29%
12 | F&C | Fraud & Corruption | 42. Percentage of cases F&C detected | 11.76%
13 | Procurement Management Capacity** | Procurement training | 43. Average number of trained procurement staff in each procuring entity | 0.66667
|  |  | 44. Percentage of procuring entity which has at least ONE trained/certified procurement staff | 66.67%
|  |  | 45. Total number of procurement persons in the organization with procurement training. | 6
*The results shown in the table are coming from sample data entered in the 13 data entry worksheets (i.e. IFB-1 to PMC-13). The implementing agency will put relevant procurement data in these 13 worksheets and the system will automatically calculate and show the results of 45 indicators.
* *Procurement training means detailed training either on goods and services or works and services or a combination of these with an approximate duration of 80 hrs (~10 working days).

## IFB-1
1. Invitation For Bid
Sl No. | Contract Package Number | Estimated cost (Mill-Tk) | Type of Review | Advertisement of Bid opportunities in newspaper |  | Require to publish in CPTU's website | Advertisement of Bid opportunities in CPTU’s website | Bids following PPA 2006 / PPR 2008 | Bid following Development Partner Rules
|  |  |  | IFB Publication | Name of Newspapers
1 | G-401 | 70 | Prior | 2010-03-01 | The Daily Galaxy, Shesh Alo | Yes | Yes |  | Yes
2 | GFP-04/01 | 20 | Post | 2010-03-05 | The Daily Galaxy, Shesh Alo | Yes | Yes | Yes
3 | G-101 | 30 | Prior | 2010-03-04 | The Daily Galaxy, Shesh Alo | Yes | No |  | Yes
4 | S-01 | 0.4 | Post | 2010-03-02 | The Daily Galaxy, Shesh Alo | No | No | Yes
5 | CMMU-19.01 | 65 | Prior | 2010-03-10 | The Daily Galaxy, Shesh Alo | Yes | Yes | Yes
6
7
8
9
10
11
12
13
14
15
Total | 5 | 4 |  |  | 5 |  | 3 | 3 | 2
Total in Percentage |  |  |  |  | 100% |  | 75% | 60% | 40%
| Note |  | automated calculation for newspaper and date

## BS-2
2. Bid Submission
Sl No. | Contract Package Number | Multiple locations submission Bids |  | Bid preparation time in open Bidding method |  |  |  | Bid time compliance | Sale of Bid documents | Bidder Participation | Bidder Participation Index | Remarks
|  | *Multiple/Single | % of multiple | IFB publication date | Bid Opening date | Days taken for Bidding/Re-bidding | Average (days)
1 | G-401 | single |  | 2010-03-01 | 2010-04-25 | 55 |  | Yes | 10 | 5 | 0.5
2 | GFP-04/01 | single |  | 2010-03-05 | 2010-03-29 | 24 |  | No | 15 | 4 | 0.26667
3 | G-101 | single |  | 2010-03-04 | 2010-04-20 | 47 |  | Yes | 12 | 10 | 0.83333
4 | S-01 | single |  | 2010-03-02 | 2010-04-02 | 31 |  | Yes | 15 | 10 | 0.66667
5 | CMMU-19.01 | single |  | 2010-03-10 | 2010-04-15 | 36 |  | Yes | 4 | 3 | 0.75
6
7
8
9
10
11
12
13
Total | 5 |  | 0% |  |  |  | 38.6 | 80% | 11 | 6 | 0.54545
*
Bid time compliance should be calculated automatically
ICB and NCB average should be separated
Note on I9: Mredha:
Note on I10: Mredha:

## BOC,BEC -3
3. Bid Opening Committee (BOC) and Bid Evaluation Committee (BEC)
Sl No. | Contract Package Number | Estimated cost (Mill-Tk) | Type of Review | Bid Opening Committee formation |  | Bid Evaluation Committee formation |  | External member in BEC
|  |  |  | Total members (Nos) | At least one Member from BEC | Total members (Nos) | Cases BEC formed by contract approving authority
1 | G-401 | 70 | Prior | 4 | Yes | 7 | Yes | 1
2 | GFP-04/01 | 20 | Post | 4 | Yes | 7 | Yes | 2
3 | G-101 | 30 | Prior | 4 | Yes | 7 | No | 2
4 | S-01 | 0.4 | Post | 3 | Yes | 6 | Yes | 2
5 | CMMU-19.01 | 65 | Prior | 5 | Yes | 10 | Yes | 6
6
7
8
9
10
11
12
13
Total | 5 |  |  |  | 100% |  | 80% | 80%
Automatic culation of compliance
* BOC/BEC is synonymous to PPR terminology TOC/TEC respectively

## BE-4
4. Bid Evaluation
Sl No. | Contract Package Number | Estimated cost (Mill-Tk) | Type of Review | Bid Opening date | Bid evaluation completion date | Bid evaluation time (days) | *Compliance of Bid evaluation time | Total bid submitted | Bid Acceptance (Responsive bids) | Ratio of responsive bid | BEC recommended for Re-Bidding | Bid Cancelled | Remarks
1 | G-401 | 70 | Prior | 2010-04-25 | 2010-07-20 | 86 | no |  | 2 |  | no | no
2 | GFP-04/01 | 20 | Post | 2010-03-29 | 2010-05-15 | 47 | no |  | 2 |  | no | no
3 | G-101 | 30 | Prior | 2010-04-20 | 2010-08-20 | 122 | no |  | 3 |  | no | no
4 | S-01 | 0.4 | Post | 2010-04-02 | 2010-12-05 | 247 | no |  | 1 |  | no | yes
5 | CMMU-19.01 | 65 | Prior | 2010-04-15 | 2010-06-20 | 66 | no |  | 3 |  | no | nol
6
7
8
9
10
11
12
13
Total | 5 |  |  |  |  | 113.6 | 0% |  | 2.2 |  | 0% | 20%
Automated calculation for compliance of bid evaluation time

## BER-5
5. Bid Evaluation Report (BER) approval
Sl No. | Contract Package Number | Estimated cost (Mill-Tk) | Type of Review | Approved Contract Cost (Mill- Tk) | Bid Evaluation Approval time |  |  | Compliance of financial delegation | Submission of evaluation report directly to contract approving authority | Case of contract award decision made within timeline by contract approving authority | Case of BER reviewed by person/committee other than contract approving authority | Higher tier approval
[5 empty] | Date of submission of BER/Purchase Proposal | Date of contract approval (Contract signing date) | days taken betn submission of BER and approval of contract
1 | G-401 | 70 | Prior | 68 | 2010-07-25 | 2010-10-20 | 87 | yes | no | yes | no | no
2 | GFP-04/01 | 20 | Post | 19.5 | 2010-05-20 | 2010-06-05 | 16 | yes | yes | yes | no | yes
3 | G-101 | 30 | Prior | 34 | 2010-08-25 | 2010-09-25 | 31 | yes | yes | yes | no | no
4 | S-01 | 0.4 | Post | 0.38 | 2010-12-10 | 2010-12-25 | 15 | yes | yes | yes | no | no
5 | CMMU-19.01 | 65 | Prior | 60 | 2010-06-25 | 2010-08-15 | 51 | yes | yes | no | no | no
6
7
8
9
10
11
12
Total | 5 | [5 empty] | 40 | 100% | 80% | 80% | 0% | 20%

## CA-6
6. Contract Award
Sl No. | Contract Package Number | Estimated cost (Mill-Tk) | Type of Review | Approved Contract Cost (Mill- Tk) | Contract Approval Date | Time taken from final approval to issuance of NOA to Bidder | Bid Opening Date | Letter of Acceptance (LOA/NOA) | No. of days taken from Bid opening to NOA/LOA | IFB publication Date | No. of days taken from IFB publication to NOA | Case of contract awards published in CPTU's website | Contract awarded within initial bid validity period | Remarks
1 | G-401 |  |  |  | 2010-10-06 | 4 | 2010-04-25 | 2010-10-10 | 168 | 2010-03-01 | 223 | yes | no
2 | GFP-04/01 |  |  |  | 2010-05-22 | 5 | 2010-03-29 | 2010-05-27 | 59 | 2010-03-05 | 83 | yes | yes
3 | G-101 |  |  |  | 2010-09-11 | 3 | 2010-04-20 | 2010-09-14 | 147 | 2010-03-04 | 194 | yes | no
4 | S-01 |  |  |  | 2010-12-11 | 17 | 2010-04-02 | 2010-12-28 | 270 | 2010-03-02 | 301 | yes | no
5 | CMMU-19.01 |  |  |  | 2010-08-01 | 2 | 2010-04-15 | 2010-08-03 | 110 | 2010-03-10 | 146 | yes | yes
6
7
8
9
10
11
12
Total | 5 |  |  |  |  | 6.2 |  |  | 150.8 |  | 189.4 | 100% | 40%
Compliance with PPR for average time
Comparison of actual and estimated cost

## D,C-7
7. Delivery/Completion
Sl No. | Contract Package Number | Estimated cost (Mill-Tk) | Type of Review | Approved Contract Cost (Mill- Tk) | Work commencement date | Schedule completion date | Work Completion days | Contract completed within the original schedule | Contract having Liquidated damage imposed for delayed completion | Contracts fully completed and accepted
1
2
3
4
5
6
7
8
9
10
11
12
Total | 0 | [6 empty] | 0% | 0% | 0%
NAV
NAP

## Pyt-8
8. Payment
Sl No. | Contract Package Number | Estimated cost (Mill-Tk) | Type of Review | Approved Contract Cost (Mill- Tk) | No. of days taken to release payment |  |  |  |  | Cases with delayed payment | Cases of Interest paid for delayed payment
[5 empty] | 1st R/A | 2nd R/A | 3rd R/A | Final | Avg (days)
1
2
3
4
5
6
7
8
9
10
11
12
Total | 0 |  |  |  | 0 | 0 | N/A | N/A | 0 | 0% | #DIV/0!
More then 4 paayments who to calculate
Porvision of interest of delayed payment

## Cmpt-9
9. Complaints
Sl No. | Contract Package Number | Estimated cost (Mill-Tk) | Type of Review | Approved Contract Cost (Mill- Tk) | Bidding Process with complaints | Complaints resulting in modification of award | Cases complaints resolved | Cases forwarded to review panel | Cases review panel's decision upheld
1 | W - 825 | 10.9 | Post | 10.89 | No | N/A | N/A | no | N/A
2 | W - 345 | 9.19 | Prior | 10.98 | Yes | No | Yes | no | N/A
3 | W - 730 | 9.329 | Prior | 8.41 | Yes | No | Yes | no | N/A
4 | W - 228 | 9.557 | Prior | 12.29 | No | N/A | N/A | no | N/A
5 | W - 434 | 11.94 | Prior | 14.202 | No | N/A | N/A | no | N/A
| W - 671 | 9.98 | Post | 11.436 | No | N/A | N/A | y | N/A
6 | W - 358 | 10.61 | Prior | 12.67 | NO | N/A | N/A | no | N/A
7 | W - 147 | 7.42 | Prior | 8.224 | Yes | No | Yes | no | N/A
8 | W - 443 | 15.625 | Prior | 15.62 | No | N/A | N/A | no | N/A
9 | W - 231 | 10.37 | Prior | 10.603 | No | N/A | N/A | no | N/A
10 | W - 435 | 12.97 | Prior | 12.99 | No | N/A | N/A | no | N/A
| W - 616 | 3.31 | Post | 3.31 | No | N/A | N/A | no | N/A
11 | W - 217 | 11.318 | Prior | 14.31 | No | N/A | N/A | no | N/A
12 | W - 403 | 34.78 | Prior | 34.778 | No | N/A | N/A | no | N/A
Total | 14 |  |  |  | 21.43% | 0% | 21.43% |  | N/A
Where complaint is resolved

## CAmt-10
10. Contract amendments
Sl No. | Contract Package Number | Estimated cost (Mill-Tk) | Type of Review | Approved Contract Cost (Mill- Tk) | Cases of Contract Amendment/variation
1 | W - 825 | 10.9 | Post | 10.89 | N/A
2 | W - 345 | 9.19 | Prior | 10.98 | N/A
3 | W - 730 | 9.329 | Prior | 8.41 | N/A
4 | W - 228 | 9.557 | Prior | 12.29 | Yes
5 | W - 434 | 11.94 | Prior | 14.202 | N/A
| W - 671 | 9.98 | Post | 11.436 | N/A
6 | W - 358 | 10.61 | Prior | 12.67 | N/A
7 | W - 147 | 7.42 | Prior | 8.224 | N/A
8 | W - 443 | 15.625 | Prior | 15.62 | N/A
9 | W - 231 | 10.37 | Prior | 10.603 | N/A
10 | W - 435 | 12.97 | Prior | 12.99 | N/A
| W - 616 | 3.31 | Post | 3.31 | N/A
11 | W - 217 | 11.318 | Prior | 14.31 | N/A
12 | W - 403 | 34.78 | Prior | 34.778 | N/A
Total | 14 |  |  |  | 7.143%

## CD-11
11. Contract dispute resolution
Sl No. | Contract Package Number | Estimated cost (Mill-Tk) | Type of Review | Approved Contract Cost (Mill- Tk) | Contracts with dispute | Contracts with unresolved Disputes
1 | W - 825 | 10.9 | Post | 10.89 |  | No
2 | W - 345 | 9.19 | Prior | 10.98 |  | No
3 | W - 730 | 9.329 | Prior | 8.41 |  | No
4 | W - 228 | 9.557 | Prior | 12.29 |  | No
5 | W - 434 | 11.94 | Prior | 14.202 |  | No
| W - 671 | 9.98 | Post | 11.436 |  | Yes
6 | W - 358 | 10.61 | Prior | 12.67 |  | No
7 | W - 147 | 7.42 | Prior | 8.224 |  | No
8 | W - 443 | 15.625 | Prior | 15.62 |  | Yes
9 | W - 231 | 10.37 | Prior | 10.603 |  | No
10 | W - 435 | 12.97 | Prior | 12.99 |  | No
| W - 616 | 3.31 | Post | 3.31 |  | No
11 | W - 217 | 11.318 | Prior | 14.31 |  | No
12 | W - 403 | 34.78 | Prior | 34.778 |  | No
Total | 14 |  |  |  |  | 14.29%

## F & C -12
12. Fraud & Corruption (F&C)
Fraud & Corruption Indicators
Type | Description
1 | Bid Securities from same bank and consecutive numbers.
2 | Bid prices (or unit rates of bill of quantities) are identical or similar to other bids
3 | Rotation of winning bidders by job, type of work or geographical area
4 | Large number of bidding documents sold but only one or a few bidders responded due to F&C practice
5 | Occurrence of Coercive practice
Sl No. | Description of work | Contract Package Number | F&C detected | Type of F&C | What steps have been taken by IA if F&C detected
1 |  | W - 825 | No
2 |  | W - 345 | No
3 |  | W - 730 | No
4 |  | W - 228 | No
5 |  | W - 434 | No
|  | W - 671 | No
6 |  | W - 358 | No
7 |  | W - 147 | No
|  | W - 333 | No
8 |  | W - 443 | No
9 |  | W - 231 | No
10 |  | W - 435 | No
|  | W - 616 | No
11 |  | W - 217 | No
|  | W-299 | Yes | 1
12 |  | W - 403 | No
13 |  | W-291 | Yes | 4
Total | 0 | 17 | 11.76%

## PMC-13
13. Procurement Management Capacity
Sl No. | Name of Implementing agencies /entities | Procurement training
|  | Number of trained procurement staff in each procuring entity | Procuring entity which has at least ONE trained/certified procurement staff | Total number of procurement persons in the organization with procurement training | Remarks
1 | XX | 1 | Yes | 1
2 | XX | 1 | Yes | 1
3 | XX | 0 | No
4 | XX | 1 | Yes | 1
5 | XX | 1 | Yes | 1
6 | XX | 1 | Yes | 1
7 | XX | 0 | No
8 | XX | 0 | No
9 | XX | 1 | Yes | 1
Total | 9 | 0.66667 | 66.67% | 6
detail of the trained staffs
who many staffs are working in procurement area